## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme | SM/07218 | Retrofitting | Providing functional house hold tap connection (FHTC) in connection with jal Jeevan Mission ( JJM and Jal Swapna Programme ) for Bairagi Village of Bairagi piped water supply scheme at Kharibari |  |  | ORD/000171/2020-2021 | 1275/SWSD | 14/08/2020 | 14/08/2025 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 32.19 | 29.04 | 90.19 | 0
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme | SM/07218 | Retrofitting | Providing functional house hold tap connection under Jal Swapno programme for Bairagi village of Duba & Gayen village of Bairagi piped water supply scheme at Khoribari block under Siliguri Sub Division, PHE Dte. SL. No. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000078/2021-2022 | 1826/SWSD | 13/01/2022 | 27/02/2022 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 35.33 | 0 | 0 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme | SM/07218 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 1668/SWSD | 28/12/2021 | 28/12/2021 | Resource Division | 2.68 | 0 | 0 | 0
Total | [13 empty] | 70.21 | 29.04 | 41.35