## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block | SM/07422 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Huchaimallick mouza and remaining part of Fakna mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 12 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000051/2021-2022 | 1222/SWSD | 01/11/2021 | 21/11/2021 | PRADIP GUHA | 16.83 | 0 | 0 | 68
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block | SM/07422 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Birsing mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000050/2021-2022 | 1221/SWSD | 01/11/2021 | 06/12/2021 | M/S MATRI CONSTRUCTION | 31.13 | 0 | 0 | 100
Total | [13 empty] | 47.96 | 0 | 0