## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block | SM/07426 | Retrofitting | Laying of new pipe line inconnection with providing functional household tap connection (FHTC) at OMI village of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000100/2022-2023 | 333/SWSD | 18/05/2022 | 28/05/2022 | UJJWAL ROY | 4.39 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block | SM/07426 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Mahasing Habitation Fokira jote Mahasing village Deomani Habitation Deomani village Nandalal Habitation Jaban jote and Mouri jote of OMI Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte (3rd CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000008/2021-2022 | 694/SWSD | 02/08/2021 | 01/09/2021 | S.K. BANIK | 27.18 | 0 | 0 | 100
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block | SM/07426 | Retrofitting | Laying bye-pass pipeline along with construction of boundary wall, development of land at head work site of OMI & adjoining w/s scheme under Siliguri Sub Division PHE Dte. |  |  | ORD/000791/2020-2021 | 1429/SWSD | 14/08/2020 | 14/08/2020 | S.K. BANIK | 24.87 | 0 | 0 | 75
Total | [13 empty] | 56.45 | 0 | 0