## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 895/SWSD | 24/08/2021 | 24/08/2021 | Resource Division | 5.77 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000306/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 5.53 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | Retrofitting | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August (01/08/24 to 13/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 |  |  | BILL/00353/2024-2025 | BP-2024-25-126 | 25/11/2024 | 25/11/2024 | SONA PETROL PUMP | 0.34 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of OCTOBER(18/10/24 to 29/10/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 |  |  | BILL/00352/2024-2025 | BP-2024-25-127 | 25/11/2024 | 25/11/2024 | SONA PETROL PUMP | 0.26 | 0 | 0 | 0
Total | [13 empty] | 143.18 | 0 | 0