## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u | SM/08295 | Retrofitting | Survey for existing water source electric connection nature of building etc. of schools,AWCs,health centres within different blocks under Siliguri Sub-Division,P.H.E Dte. | Assistant Engineer(Civil) |  | ORD/000230/2022-2023 | 544/SSD | 19/12/2022 | 03/01/2023 | ROYAL ENTERPRISE | 1.02 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u | SM/08295 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C.on hire basis including driver for Assistant Engineer-I , Siliguri W/S Division, P.H.E. Dte. Dist. Darjeeling (with valid Taxi permit ). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000411/2023-2024 | 284/SWSD | 06/02/2024 | 06/08/2024 | SUDIP BASAK | 0.88 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u | SM/08295 | Retrofitting | Further continuation order for hiring of 01 (one) no maxi cab with engine capacity less than or equal to 2000 CC with air condition for the Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte for the period from 01.09.2023 to 31.12.2023 (For Executive Engineer, Siliguri W/S Division, P.H.E. Dte. i.e 04 (four) months. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000259/2023-2024 | 1492/SWSD | 31/08/2023 | 31/12/2023 | SUBIR CH. CHOWDHURY | 0.59 | 0 | 0 | 0
Total | [13 empty] | 2.49 | 0 | 0