## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin | SM/09078 | Retrofitting | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000089/2022-2023 | 386/SSD | 20/07/2022 | 09/08/2022 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin | SM/09078 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of July (16/07/24 to 26/07/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 |  |  | BILL/00354/2024-2025 | BP-2024-25-129 | 25/11/2024 | 25/11/2024 | SONA PETROL PUMP | 0.32 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin | SM/09078 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August(20/08/24 to 29/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 |  |  | BILL/00357/2024-2025 | BP-2024-25-128 | 25/11/2024 | 25/11/2024 | SONA PETROL PUMP | 0.35 | 0 | 0 | 0
Total | [13 empty] | 1.7 | 0 | 0