## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D | SM/09204 | Augmentation | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000089/2022-2023 | 386/SSD | 20/07/2022 | 09/08/2022 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D | SM/09204 | Augmentation | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2024-2025 | 2931/SWSD | 30/10/2024 | 14/12/2024 | ARUN KUMAR SHRIVASTAVA | 49.08 | 0 | 0 | 0
Total | [13 empty] | 50.11 | 0 | 0