## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000891/2021-2022 | BP-2021-22-109 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 31.44 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000305/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 10.86 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying distribution system (Part-F) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-F) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000144/2021-2022 | 2440/SWSD | 21/03/2022 | 30/04/2022 | M/S ASHIRBAD ENTERPRISE | 33.08 | 0 | 0 | 60
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 29/10/2022 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 02 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000057/2022-2023 | 862/SWSD | 21/07/2022 | 04/10/2022 | M/S UTPAL CHAKRABORTY & CO. | 82.68 | 0 | 0 | 83
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000059/2022-2023 | 864/SWSD | 21/07/2022 | 25/08/2022 | SHIVNATH DEY | 25.22 | 0 | 0 | 90
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000025/2022-2023 | 536/SWSD | 16/06/2022 | 21/07/2022 | SHIVNATH DEY | 25.22 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 11/01/2023 | G. TECH INDIA | 3.21 | 0 | 0 | 100
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1445/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 12.16 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 2171/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 42.81 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | New Service Connection Charge for AUGUMENTATION OF THAKURGANJ,T/W No - I W/S Scheme, under BIDHANNAGAR CCC, [APPLICATION NO. 4003058220, Reference ID : 402933259] |  |  | BILL/00752/2022-2023 | BP/22-23/156 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying distribution system (Part-E) Erection of Iron Elimination Plant allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-E) at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000143/2021-2022 | 2439/SWSD | 21/03/2022 | 04/06/2022 | M/S DEBRAJ ENTERPRISE | 85.61 | 0 | 0 | 85
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2022-2023 | 107/NMD | 03/02/2023 | 05/03/2023 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 0 | 100
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Construction of 350 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging Height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Thakurganj at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL.NO. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000013/2022-2023 | 273/SWSD | 06/05/2022 | 01/06/2025 | HIMADRI DAM & CO. | 158.69 | 0 | 0 | 60
16 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Construction of Pump House with toilet, plinth protection etc. installation of IEP and Boundary Wall at Thakurganj of THAKURGANJ Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000037/2023-2024 | 646/SWSD | 15/06/2023 | 27/01/2024 | HIMADRI DAM & CO. | 49.26 | 0 | 0 | 35
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Acceptance cum Work Order for Additional Work for functional house hold tap connection (FHTC) at Agumentation Thakurganj and Adjoining Mouzas water Supply Scheme under Phansidewa Block under Siliguri Sub Division , P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000012/2025-2026 | 1238/SWSD | 24/04/2025 | 24/05/2025 | VIJAY KUMAR ARORA | 13.11 | 0 | 0 | 0
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) and rising main at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000058/2022-2023 | 863/SWSD | 21/07/2022 | 02/11/2025 | AKASH ENTERPRISE | 122.09 | 0 | 0 | 2
Total | [13 empty] | 884.65 | 0 | 0