## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000892/2021-2022 | BP-2021-22-110 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 28.3 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000304/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.73 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-B) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 08. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000137/2021-2022 | 2434//SWSD | 21/03/2022 | 20/05/2022 | S.K. BANIK | 68.28 | 35.92 | 52.6 | 65
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-C) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 09. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000138/2021-2022 | 2435/SWSD | 21/03/2022 | 10/05/2022 | S.K. BANIK | 53.92 | 12.87 | 23.87 | 25
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Soil Investigation of Pauchkelguri PWSS for Construction of 200 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000091/2022-2023 | 388/SSD | 20/07/2022 | 09/08/2022 | R.B.TESTING | 1.02 | 0 | 0 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Construction of Pump House (5.4 X 3.60) size with (1.35 X 2.10 M) size toilet, plinth protection etc. and boundary wall at Khopalasi of PAUCHAKELGURI Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000038/2023-2024 | 642/SWSD | 15/06/2023 | 30/07/2023 | U.K CONSTRUCTIONS | 12.89 | 5.83 | 45.24 | 50
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 2172/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 39.61 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1448/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 9.74 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. I under MATIGARA CCC [APPLICATION NO. 4003058425 ; Reference ID : 402932707] |  |  | BILL/00003/2023-2024 | BP/23-24/05 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. II under MATIGARA CCC [APPLICATION NO. 4003058421 ; Reference ID : 402932706] |  |  | BILL/00002/2023-2024 | BP/23-24/05 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | New Service Connection Charge for PACHKELGURI, T/W I, under MATIGARA CCC, [APPLICATION NO. 4003199222, Reference ID : 403050473] |  |  | BILL/00582/2023-2024 | BP/23-24/67 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0 | 0
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Construction of 200 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Pauchakelguri and adjoining mouzas water supply scheme within Matigara block under Siliguri Sub Division, PHE Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000007/2022-2023 | 176/SWSD | 22/04/2022 | 19/10/2022 | S.K. BANIK | 126 | 79.72 | 63.26 | 35
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 29/10/2022 | M/S NIRANJAN SARKAR | 46.36 | 22.26 | 48.02 | 100
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and Boundary Wall at Jhaguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000175/2023-2024 | 1203/SWSD | 10/08/2023 | 24/09/2023 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.45 | 10.93 | 81.32 | 100
16 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Infrastructure Cost for PACHKELGURI, T/W No. I, under MATIGARA CCC [APPLICATION NO. 100000084014 , Reference ID : 860275184] |  |  | BILL/01785/2023-2024 | BP/23-24/286 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 27.56 | 0 | 0 | 0
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-D) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 10. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000139/2021-2022 | 2436/SWSD | 21/03/2022 | 29/06/2026 | U.K CONSTRUCTIONS | 73.9 | 62.49 | 84.55 | 65
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-E) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 09. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000063/2022-2023 | 868/SWSD | 21/07/2022 | 01/04/2025 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 81.94 | 54.47 | 66.48 | 70
19 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Acceptance cum work order "Construction of Pump House (3 NOS) (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. Rising Main and Boundary Wall at Pauchakelguri ,Khopalasi and Jhauguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000321/2023-2024 | 604/SWSD | 06/03/2024 | 11/12/2024 | M/S JAYDEV JHA | 28.86 | 0 | 0 | 60
20 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000246/2024-2025 | 1524/NMD | 03/09/2024 | 16/10/2025 | ALPHA ENTERPRISE | 11.91 | 0 | 0 | 75
21 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME ,TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 547/NMD | 15/05/2023 | 02/04/2025 | ALPHA ENTERPRISE | 23.49 | 20.19 | 85.94 | 90
Total | [13 empty] | 793.6 | 304.68 | 38.39