## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000303/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 18.84 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000896/2021-2022 | BP-2021-22-114 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 64.05 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000002/2022-2023 | 36/SWSD | 07/04/2022 | 16/07/2022 | VIJAY KUMAR ARORA | 198.7 | 179.3 | 90.23 | 95
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) of Distribution Pipeline (Part-D) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000003/2022-2023 | 35/SWSD | 07/04/2022 | 06/07/2022 | ANUP BASU | 123.58 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | `Continuation of Hiring of 1(one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E Dte. from 1.03.2022 to 31.08.2022 (with Engine Capacity less than or equal to 2000 CC) Vehicle no. WB76A 4921) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000220/2021-2022 | 112/SSD | 28/02/2022 | 31/08/2022 | SUDIP BASAK | 0.88 | 2.09 | 237.08 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 28.02.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. SIX MONTHS. | Assistant Engineer(Civil) |  | ORD/000197/2022-2023 | 1236/SWSD | 31/08/2022 | 28/02/2023 | HIMADRI DAM | 0.88 | 1.54 | 174.48 | 100
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Constuction of Pump House (3.6*3.0m) at Kalam 3rd site under Augmentation of Kalam piped water supply scheme under Matigara Block Darjeeling district in connection with Jal jeevan Mission under Siliguri Sub-division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000021/2023-2024 | 268/SSD | 05/06/2023 | 20/07/2023 | K.K.GHOSH & CO. | 4.75 | 4.75 | 100 | 100
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 2178/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 84.79 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1447/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 13.8 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | New Service Connection Charge for KALAM, T/W II, under SHIVMANDIR CCC [APPLICATION NO. 4003119079 ; Reference ID : 402986632] |  |  | BILL/00005/2023-2024 | BP/23-24/03 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | New Service Connection Charge for KALAM, T/W III, under SHIVMANDIR CCC [APPLICATION NO. 4003119111 ; Reference ID : 402986652] |  |  | BILL/00004/2023-2024 | BP/23-24/03 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) at Distribution Pipeline (Part-C) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000103/2021-2022 | 2081/SWSD | 03/02/2022 | 05/01/2023 | KAMAL GHOSH | 63.4 | 48.53 | 76.54 | 92
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 29/10/2022 | M/S NIRANJAN SARKAR | 46.36 | 10.98 | 23.69 | 100
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Construction of Pump House(3.6 X 3.0 m), at Kalam 4th Site under Augmentation of Kalam piped water supply Scheme under Matigara Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000017/2023-2024 | 194/SSD | 04/05/2023 | 18/06/2023 | K.K.GHOSH & CO. | 4.75 | 4.75 | 100 | 95
16 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , TW No II & III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 551/NMD | 15/05/2023 | 14/06/2023 | SARKAR ELECTRIC | 23.37 | 23.25 | 99.49 | 100
17 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Supply & delivery of CIDF Specials Under JJM project at Kalam W/S Scheme in the dist of Darjeeling. | Assistant Engineer | Junior Engineer | ORD/001643/2023-2024 | 383/SMSD | 07/03/2024 | 14/03/2024 | B.B. CONCERNED | 0.9 | 0.9 | 100 | 100
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Acceptance cum work order for construction of blower room, iron elimination plant, boundary wall at Kalam Piped Water Supply Scheme under Matigara block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000250/2023-2024 | 35/SWSD | 08/01/2024 | 31/01/2026 | SUBIR CH. CHOWDHURY | 63.98 | 0 | 0 | 60
19 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | Augmentation | Work Order for Construction of 200 Cu.M capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site including rising mains and distribution system (Part-A) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Kalam & adjoining mouza's water supply scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000236/2023-2024 | 2354/SWSD | 15/12/2023 | 01/03/2026 | SHRI ANNAPURNA DISTRIBUTORS | 156.84 | 82.76 | 52.77 | 50
Total | [13 empty] | 1002.71 | 358.84 | 35.79