## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | SHIFTING OF EXISTING TRANSFORMER ALONG WITH 11 KV HOTH LINE. ( REF ID: 860242115 AND APPLICATION ID : 100000052425 ) |  |  | VCH/000185/2022-2023 |  | 22/06/2022 | 22/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.85 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000894/2021-2022 | BP-2021-22-112 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 62.77 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000302/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 12.12 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-E) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000095/2021-2022 | 2080/SWSD | 03/02/2022 | 19/04/2022 | HIMADRI DAM & CO. | 70.68 | 34.19 | 48.38 | 50
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2021-2022 | 2077/SWSD | 03/02/2022 | 04/04/2022 | SUDIP BASAK | 66.67 | 23.85 | 35.78 | 52
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Soil Investigation of Salbari PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000108/2022-2023 | 392/SSD | 20/07/2022 | 09/08/2022 | SUBIR CH. CHOWDHURY | 1.03 | 0 | 0 | 100
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 29/10/2022 | GANPATI CONSTRUCTION CO | 46.34 | 5.78 | 12.47 | 100
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) |  | ORD/000170/2022-2023 | 1330/SWSD | 14/09/2022 | 09/10/2022 | M/S K. R. S. CONSTRUCTION | 15.45 | 4.45 | 28.83 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Construction of 300 cu.m. capacity RCC Elevated Reservoir, 20 mtrs. staging height at the head works site including rising main and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of SALBARI CHHAT, PRATHAM KHANDA, PANCHANAI, NUNU BAIRAGI, MAHATRAM, UDAYSING MOUZA'S (Partially) of SALBARI and adjoining mouza's Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000105/2021-2022 | 2202/SWSD | 17/02/2022 | 16/08/2022 | SUBIR CH. CHOWDHURY | 125.67 | 114.98 | 91.5 | 100
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000149/2021-2022 | 2534/SWSD | 29/03/2022 | 10/04/2022 | RUPA PRASAD | 1.48 | 0.97 | 65.13 | 100
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Repair and renovation of the Head Work site Pump House (3.65 m X 2.45 m) size and boundary wall at Head work site allied with additional works like shifting of Rising Main and drain under Augmentation of SALBARI W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000002/2023-2024 | 53/SWSD | 10/04/2023 | 10/05/2023 | SUBIR CH. CHOWDHURY | 9.84 | 7.51 | 76.24 | 75
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 2176/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 73.29 | 0 | 0 | 0
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1446/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 9.7 | 0 | 0 | 0
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Hiring 1 no. diesel consumed luxury vehicle on monthly basis preferably Maxi Cab (with A/C) for Deputy Superintending Engineer, NBC-I, PHE Dte. |  |  | BILL/00068/2022-2023 | BP-2022-23-132 | 20/02/2023 | 20/02/2023 | OM TRAVELS | 1.95 | 0 | 0 | 0
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
16 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Hiring of 1(one) no. Mariti van (non A/C) for the office of the Superintending Engineer, NBC-I , PHE Dte. period from Septenber,October & November 2022 |  |  | BILL/00041/2022-2023 | BP-2022-23-114 | 09/02/2023 | 09/02/2023 | RUPA PRASAD | 0.8 | 0 | 0 | 0
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000094/2021-2022 | 2079/SWSD | 03/02/2022 | 15/03/2022 | BUDDHADEV NAG | 30.7 | 23.48 | 76.5 | 60
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000093/2021-2022 | 2078/SWSD | 03/02/2022 | 04/04/2022 | M/S G.C. CONSTRUCTION & CO. | 65.37 | 45.57 | 69.71 | 80
19 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Acceptance cum work order for construction of 4th Tubewell Pump House (3.60 m X 2.40 m) allied with rising main and boundary wall under Augmentation of Salbari W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000181/2023-2024 | 1793/SWSD | 29/09/2023 | 15/09/2024 | M/S UNIQUE13 | 14.26 | 8.35 | 58.59 | 70
20 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | New Service Connection Charge for SALBARI, T.W. No. IV under MATIGARA CCC [APPLICATION NO. 4003194765 ; Reference ID : 403046874] |  |  | BILL/02009/2023-2024 | BP/23-24/309 | 16/02/2024 | 16/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0 | 0
21 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 1395/NMD | 09/08/2023 | 02/01/2025 | M/S SAJAHAN CHOWDHURY | 12.99 | 12.06 | 92.82 | 100
Total | [13 empty] | 758.46 | 281.19 | 37.07