## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000890/2021-2022 | BP-2021-22-108 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 230.79 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000301/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 1.32 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Laying distribution system (Part-F) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-F) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000136/2021-2022 | 2433/SWSD | 21/03/2022 | 05/05/2022 | BUDDHADEV NAG | 49.84 | 25.91 | 51.97 | 60
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Soil Investigation of Lahugaon Z II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000093/2022-2023 | 390/SSD | 20/07/2022 | 09/08/2022 | D.P. ENTERPRISE | 1.03 | 1.03 | 100 | 100
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Soil Investigation of Lahugaon Z I PWSS for Construction of 400 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000092/2022-2023 | 389/SSD | 20/07/2022 | 09/08/2022 | M/S PRANTIK ASSOCIATES | 1.02 | 1.02 | 100 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 2169/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 313.89 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1449/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 25.7 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. |  |  | BILL/00110/2023-2024 | BP-2023-24-41 | 28/07/2023 | 28/07/2023 | SUDIP BASAK | 2.24 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | HIRING OF 1 (ONE) NO. WELL MAINTAINED DIESEL CONSUMED LUXURY CAB ON MONTHLY HIRED BASIS PREFERABLY MAXI CAB (A/C) WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC FOR OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHER ZONE, P.H.E. DTE. VIVEKANANDA BHAWAN (2ND FLOOR) HILL CART ROAD, SILIGURI (FOR ASSISTANT CHIEF ENGINEER, NORTHERN ZONE (CIVIL), P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 31.10.2022 i.e. 2 (TWO) MONTHS. |  |  | BILL/00067/2022-2023 | BP-2022-23-131 | 20/02/2023 | 20/02/2023 | OM TRAVELS | 1.08 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | New Service Connection Charge for LAHUGAON, KUMARTULI, T.W. No. I under BIDHANNAGAR CCC, [APPLICATION NO. 4003194405, Reference ID : 403046890] |  |  | BILL/00590/2023-2024 | BP/23-24/74 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0 | 0
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Acceptance cum work order "Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and two nos Pump House (3600mm x 2400mm x 3300mm height) with toilet (2100mm x 1350mm) sanitary and plumbing arrangement along with verandah (3975mm x 1500mm) having plinth height 600m m. and construction of Boundary Wall at Three Different Site Pump House Site and Iron Elemination Plant Under Lohugaon (Z-II) at Lahugaon (Z-II) Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000320/2023-2024 | 603/SWSD | 06/03/2024 | 02/01/2026 | SHYAMAL NATH | 68.77 | 0 | 0 | 60
13 | DARJEELING |  | Central Drilling | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000030/2024-2025 | 560/CDD | 06/08/2024 | 06/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 7 | 46.53 | 10
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Charges for additional quotation For lahugaon PWSS (Near Kumar tuli),Z-II,Tw-II under NMD PHE dte. Application no- 4003320704 Ref ID- 403147041 For Additional Quotation Application ID- 100000114620 Ref ID- 860308530 |  |  | BILL/00643/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.88 | 0 | 0 | 0
15 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Infrastructure Cost for LAHUGAON T/W No.II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320700, Reference ID : 403147042] |  |  | BILL/02022/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
16 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Infrastructure Cost for LAHUGAON T/W No. II, ZONE-II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320704, Reference ID : 403147041] |  |  | BILL/02023/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.35 | 0 | 0 | 0
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Laying distribution system (Part-B) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-B) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000133/2021-2022 | 2430/SWSD | 21/03/2022 | 30/05/2026 | SUBIR CH. CHOWDHURY | 64.88 | 37.49 | 57.78 | 65
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Laying distribution system (Part-C) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-C) of Lahugaon (Zone-1) and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000134/2021-2022 | 2431/SWSD | 21/03/2022 | 01/01/2026 | AKASH ENTERPRISE | 53.99 | 28.79 | 53.32 | 60
19 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Laying distribution system (Part-D) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-D) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000135/2021-2022 | 2432/SWSD | 21/03/2022 | 10/05/2022 | M/S FULBARI CONSTRUCTION CO. | 53.41 | 29.71 | 55.63 | 65
20 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Construction of 400 cu.m. capacity RCC Over Head Reservoir, 20 mtrs Staging height and rising mains with laying distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Lohugaon (Zone-I) and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. Sl. No. 07. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000062/2022-2023 | 867/SWSD | 21/07/2022 | 20/11/2025 | PALLAB BHOWAL | 159.67 | 100.35 | 62.85 | 70
21 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Construction of 300 cum capacity Over Head Reservoir, Laying Distribution System with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewells (H/W, 2nd & 3rd sites) by ODEX-165 method of drilling under Augmentation of Lohugaon (Zone-II) piped water supply scheme under Jal Swapna/JJM works within Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000269/2022-2023 | 2376/SWSD | 24/01/2023 | 02/05/2025 | FAIRDEAL ASSOCIATES | 400.24 | 85.82 | 21.44 | 70
22 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME, TW No. III (Zone-I), TW-I and II (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000666/2023-2024 | 1480/NMD | 17/08/2023 | 01/10/2025 | ANUP BASU | 34.42 | 0 | 0 | 70
23 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | Augmentation | Supplying. Fabrication, Erection of IRON ELEMINATION PLANT at Lohugaon (Z-1) and construction of Blower Room at pump house site at Lohugaon water Supply Scheme Under Siliguri Sub division, P.H.E DTE. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000138/2024-2025 | 2532/SWSD | 13/09/2024 | 13/10/2024 | PALLAB BHOWAL | 15.2 | 0 | 0 | 0
Total | [13 empty] | 1639.03 | 317.13 | 19.35