## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000300/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.92 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000889/2021-2022 | BP-2021-22-107 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 162.17 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying distribution system (Part-D) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000146/2021-2022 | 2442/SWSD | 21/03/2022 | 30/04/2022 | AKASH ENTERPRISE | 41.47 | 32.72 | 78.91 | 80
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying distribution system (Part-E) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 12. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000147/2021-2022 | 2443/SWSD | 21/03/2022 | 20/05/2022 | KAMAL GHOSH | 60.01 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000027/2022-2023 | 538/SWSD | 16/06/2022 | 26/07/2022 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000061/2022-2023 | 866/SWSD | 21/07/2022 | 30/08/2022 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000026/2022-2023 | 537/SWSD | 16/06/2022 | 31/07/2022 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Sinking of 04(four) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different Zones (as mentioned in ANNEXURE-A) of Uttar Bagdogra Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000249/2022-2023 | 2164/SWSD | 30/12/2022 | 29/01/2023 | K.R.ENTERPRISE | 32.57 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying distribution system (Part-C) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000145/2021-2022 | 2441/SWSD | 21/03/2022 | 10/05/2022 | NARAYAN CH GHOSH | 57.37 | 15.03 | 26.19 | 60
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000060/2022-2023 | 865/SWSD | 21/07/2022 | 04/09/2022 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 11/01/2023 | G. TECH INDIA | 3.21 | 0.64 | 20 | 100
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MARUTI VAN (NON A/C) FOR THE SUPERINTENDING ENGINEER, NORTH BENGAL CIRCLE-I, P.H.E. DTE. PERIOF FROM 01.04.2023 TO 30.04.2023 i.e. 1 (ONE) MONTHS. VEHICLE NO. WB 73 B/1911. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000332/2022-2023 | 2987/SWSD | 28/03/2023 | 28/04/2023 | RUPA PRASAD | 0.12 | 0.29 | 236.66 | 100
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 2170/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 225.89 | 0 | 0 | 0
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1450/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 9.68 | 0 | 0 | 0
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
16 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Construction of 400 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants ,Boundary Walls including Functional Household Tap Connections for Augmentation of UTTAR BAGDOGRA Piped Water Supply Scheme (Zone - I & II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000110/2023-2024 | 1155/SWSD | 09/08/2023 | 26/03/2026 | MAHADEO PRASAD AGARWAL & CO | 495.4 | 0 | 0 | 0
17 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III, IV and (Zone-II) TW-I,III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000756/2023-2024 | 1584/NMD | 08/09/2023 | 08/10/2023 | SUMON ELECTRICAL | 46.7 | 35.43 | 75.86 | 75
18 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | Augmentation | Electric quotation for new service connection at t.w no- i,z-ii of Uttar Bagdogra w/s scheme, in the dist. Darjeeling. |  |  | BILL/01348/2024-2025 | BP/24-25/217 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.91 | 0 | 0 | 0
Total | [13 empty] | 1466.05 | 84.11 | 5.74