## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Continuation order for hiring of 1 (one) no. well maintained diesel consumed luxury cab on monthly hired basis preferably MAXI CAB (A/C) with engine capacity less than or equal to 2000 CC for office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte., Vivekananda Bhawan (2nd floor) Hill Cart Road, Siliguri (for Assistant Chief Engineer, Northern Zone (Civil), P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000262/2021-2022 | 2269/SWSD | 24/02/2022 | 02/03/2022 | OM TRAVELS | 0.88 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 2012/SWSD | 14/12/2022 | 14/12/2022 | Resource Division | 7.18 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000888/2021-2022 | BP-2021-22-106 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.99 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000298/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.4 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2022-2023 | 1328/SWSD | 14/09/2022 | 09/10/2022 | RANJEET SINGH BENIWAL | 15.46 | 0 | 0 | 88
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Laying distribution system (Part-A) at Tari habitation for Augmentation of Bairatisal and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. Sl. No. 12. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000065/2022-2023 | 870/SWSD | 21/07/2022 | 14/10/2022 | M/S G.C. CONSTRUCTION & CO. | 92.37 | 79.72 | 86.31 | 90
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Soil Investigation of Bairatisal Zone III PWSS for Construction of 600 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000109/2022-2023 | 393/SSD | 20/07/2022 | 09/08/2022 | SUBIR CH. CHOWDHURY | 1.03 | 1.01 | 97.61 | 100
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 2174/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 112.07 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1452/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 28.55 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. II, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058171, Reference ID : 402932779] |  |  | BILL/00050/2022-2023 | BP/22-23/123 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. I, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058151, Reference ID : 402932775] |  |  | BILL/00049/2022-2023 | BP/22-23/123 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
13 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - III (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000796/2022-2023 | 110/NMD | 03/02/2023 | 05/03/2023 | B.B. CONCERNED | 23.55 | 23.48 | 99.71 | 100
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | Augmentation | Construction of 600 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising mains, distribution system, pump house (3.65 X 2.45) size, IEP, boundary wall and providing Functional Household Tap Connection (FHTC) for augmentation of BAIRATISAL and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. SL. NO. B. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000149/2022-2023 | 970/SWSD | 01/08/2022 | 31/07/2025 | M/S KAMAK ENGINEERS & CO | 584.1 | 191.88 | 32.85 | 90
Total | [13 empty] | 1137.27 | 296.08 | 26.03