## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Chamta W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 04. |  | Junior Engineer (Civil) | ORD/000111/2021-2022 | 831/SWSD | 13/08/2021 | 03/09/2021 | ENVIROTECH SOLUTIONS | 1.97 | 1.97 | 100 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000895/2021-2022 | BP-2021-22-113 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 32.46 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000297/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.52 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height including laying distribution system, 400 Nos. FHTC (Part-A) for Chamta and adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000014/2022-2023 | 274/SWSD | 06/05/2022 | 02/11/2022 | ANUP BASU | 170.09 | 68.13 | 40.06 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Laying distribution system of pipeline (Part-B) at Chamta and adjoining mouzas Water Supply Scheme withinMatigara block under Siliguri Sub Division, P.H.E. Dte. (Part-B). (2ND CALL). Sl. No. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000069/2022-2023 | 874/SWSD | 21/07/2022 | 14/10/2022 | DEBASHIS SINHA | 109.33 | 75.13 | 68.72 | 75
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Laying distribution system of pipeline at Jhauguri at Chamta and adjoining mouzas Water Supply Scheme under Matigara block under Siliguri Sub Division, P.H.E Dte.(Part E). Sl. No. 17. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000087/2022-2023 | 860/SWSD | 21/07/2022 | 04/10/2022 | BISWADEEP CONSTRUCTION | 71.84 | 57.16 | 79.57 | 92
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 2177/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 43.55 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1454/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 14.43 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. I under MATIGARA CCC, [APPLICATION NO. 4003058415, Reference ID : 402932670] |  |  | BILL/00042/2022-2023 | BP/22-23/124 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. II under MATIGARA CCC, [APPLICATION NO. 4003049182, Reference ID : 402926291] |  |  | BILL/00043/2022-2023 | BP/22-23/124 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Laying distribution system of pipeline (Part-C) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-C). (2ND CALL). Sl. No. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000070/2022-2023 | 875/SWSD | 21/07/2022 | 04/10/2022 | M/S UTPAL CHAKRABORTY & CO. | 78.93 | 66.1 | 83.75 | 70
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Laying distribution system of pipeline (Part-D) at Chamta & adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-D). Sl. No. 13. |  | Junior Engineer (Civil) | ORD/000066/2022-2023 | 871/SWSD | 21/07/2022 | 09/10/2022 | NARENDRA KUMAR | 89.17 | 66.87 | 74.99 | 80
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 29/10/2022 | M/S NIRANJAN SARKAR | 46.36 | 4.86 | 10.48 | 100
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Laying distribution system of pipeline (Part-E) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-E). (2ND CALL) Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000071/2022-2023 | 876/SWSD | 21/07/2022 | 05/03/2025 | SUBIR CH. CHOWDHURY | 104.02 | 99.07 | 95.24 | 92
16 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000795/2022-2023 | 109/NMD | 03/02/2023 | 05/03/2023 | MAA ENTERPRISES | 10.96 | 9.52 | 86.82 | 100
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | Augmentation | Soil Investigation of Champta PWSS for Construction of 350 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000107/2022-2023 | 391/SSD | 20/07/2022 | 09/08/2022 | G. MITRA & ASSOCIATES | 1.03 | 0 | 0 | 90
Total | [13 empty] | 909.24 | 448.81 | 49.36