## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Bairatisal W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000113/2021-2022 | 833/SWSD | 13/08/2021 | 07/09/2021 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000893/2021-2022 | BP-2021-22-111 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.2 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000296/2022-2023 |  | 08/08/2022 | 08/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.3 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2022-2023 | 1328/SWSD | 14/09/2022 | 09/10/2022 | RANJEET SINGH BENIWAL | 15.46 | 0 | 0 | 88
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) |  | ORD/000170/2022-2023 | 1330/SWSD | 14/09/2022 | 09/10/2022 | M/S K. R. S. CONSTRUCTION | 15.45 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1453/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 27.72 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 130/SWSD | 13/04/2022 | 13/04/2022 | Resource Division | 14.63 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 2173/SWSD | 11/02/2022 | 11/02/2022 | Resource Division | 34.95 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Hiring 1 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (WITH AIR CONDITION ) fore office of the Executive Engineer, Siliguri W/S division PHE Dte. for the period from 01.09.2021 to 28.02.2022 |  |  | BILL/00051/2022-2023 | BP-2022-23-119 | 20/02/2023 | 20/02/2023 | SUBIR CH. CHOWDHURY | 1.5 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 13/03/2023 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | New Service Connection Charge for AUG BAIRATISAL,T/W No. II,ZONE-II under SHIVMANDIR CCC [APPLICATION NO. 4003312875 , Reference ID : 403140527] |  |  | BILL/01917/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.31 | 0 | 0 | 0
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | New Service Connection Charge for AUG OF BAIRATISAL, T/W No. I, ZONE-II, under SHEVMANDIR CCC [APPLICATION NO. 4003312877 , Reference ID : 403140528] |  |  | BILL/01916/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.29 | 0 | 0 | 0
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Construction of 550 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying Rising Main, laying distribution pipeline with Functional household tap connection (FHTC), construction of 2 (two) nos. Pump House (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos tube well (ODEX-165 method) and boundary wall for BAIRATISAL PWSS (Zone-II), Block Matigara Dist. Darjeeling under Siliguri W/S Division, PHE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000118/2023-2024 | 1204/SWSD | 11/08/2023 | 16/09/2025 | BRM DEVELOPERS | 527.89 | 0 | 0 | 20
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - II (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000797/2022-2023 | 111/NMD | 03/02/2023 | 01/08/2025 | CHOWDHURY AND BASU ENTERPRISE | 20.36 | 0 | 0 | 100
Total | [13 empty] | 861.19 | 0 | 0