## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Naxalbari W/S Scheme at Naxalbari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 02. |  | Junior Engineer (Civil) | ORD/000109/2021-2022 | 819/SWSD | 13/08/2021 | 07/09/2021 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 0 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2042/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 131.38 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Construction of Pump House (3.65 X 2.45) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. at Kamala zone of Naxalbari Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000019/2022-2023 | 307/SWSD | 10/05/2022 | 29/06/2022 | S.G.CONSTRUCTION | 4.15 | 0 | 0 | 100
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supplying, fabrication, erection on subitable RCC foundation and commissioning with 3 (three) months trial run of pressure type Iron Removal Plant with bower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E. Plant with surface drain of required length at Budhkaran Zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 15 cu.m./hr.). SL. NO. 13. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000140/2021-2022 | 2437/SWSD | 21/03/2022 | 05/05/2022 | SUBIR CH. CHOWDHURY | 13.81 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dayaram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000113/2022-2023 | 283/SSD | 26/05/2022 | 25/07/2022 | SHREYANSH AUTOMOBILE | 4.17 | 0 | 0 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Chhota Maniram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000111/2022-2023 | 281/SSD | 26/05/2022 | 25/07/2022 | A.B. GANAPATI CONSTRUCTION | 4.17 | 0 | 0 | 100
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Rathkhola Bhimram Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 15 Cu.M./hr.) Sl. No. 08. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000078/2022-2023 | 851/SWSD | 21/07/2022 | 04/09/2022 | DEBRAJ ENTERPRISE | 13.82 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Dhakna Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 20 Cu.M./hr.) Sl. No. 09. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000079/2022-2023 | 852/SWSD | 21/07/2022 | 04/09/2022 | SUBIR CH. CHOWDHURY | 14.66 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supplying, fabrication, erection on suitable RCC foundation and commissioning with 3(three) months trial run of pressure type Iron Removal Plant with blower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Tutaram zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 30 cu.m./hr.) SL. NO. 11. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000030/2022-2023 | 542/SWSD | 16/06/2022 | 31/07/2022 | MAA ENTERPRISE | 16.52 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000149/2021-2022 | 2534/SWSD | 29/03/2022 | 10/04/2022 | RUPA PRASAD | 1.48 | 0 | 0 | 100
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dhakna zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000112/2022-2023 | 282/SSD | 26/05/2022 | 25/07/2022 | M/S S.P. BISWAS | 4.18 | 0 | 0 | 100
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Rathkhola - Bhimram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000110/2022-2023 | 280/SSD | 26/05/2022 | 25/07/2022 | M/S S.P. BISWAS | 4.18 | 0 | 0 | 60
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1455/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 53.04 | 0 | 0 | 0
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | New Service Connection Charge for RATHKHOLA BHIMRAM W/S Scheme, T/W No. III, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049742, Reference ID : 402926292] |  |  | BILL/00045/2022-2023 | BP/22-23/125 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
15 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | New Service Connection Charge for NAXALBARI PWSS (DHAKNA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105319 ; Reference ID : 402974350] |  |  | BILL/00009/2023-2024 | BP/23-24/04 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
16 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Hiring of Vehicle for the office of the Assistant Engineer under Siliguri Sub-division ,P.H.E dte |  |  | BILL/00026/2022-2023 | BP-2022-23-109 | 18/01/2023 | 18/01/2023 | SUDIP BASAK | 0.38 | 0 | 0 | 0
17 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | New Service Connection Charge for CHHOTO MONIRAM KALUAJOTE W/S Scheme, T/W No. II, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049226, Reference ID : 402926293] |  |  | BILL/00044/2022-2023 | BP/22-23/125 | 16/01/2023 | 16/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
18 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | New Service Connection Charge for NAXALBARI PWSS (KAMALA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105316 ; Reference ID : 402974351] |  |  | BILL/00008/2023-2024 | BP/23-24/04 | 26/04/2023 | 26/04/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
19 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Kamala (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Tutaram Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 15. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000004/2022-2023 | 38/SWSD | 07/04/2022 | 19/04/2023 | ARUN KUMAR SHRIVASTAVA | 137.11 | 0 | 0 | 60
20 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying Distribution System and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Dayaram (Part), Kamala (Part) & Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kamala Zone) within Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000064/2022-2023 | 869/SWSD | 21/07/2022 | 07/01/2023 | NARAYAN CH GHOSH | 69.9 | 0 | 0 | 90
21 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dayaram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000074/2022-2023 | 847/SWSD | 21/07/2022 | 04/02/2023 | M/S G.C. CONSTRUCTION & CO. | 83.65 | 0 | 0 | 2
22 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dhakna Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000075/2022-2023 | 848/SWSD | 21/07/2022 | 29/09/2022 | BUDDHADEV NAG | 67.02 | 0 | 0 | 100
23 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supply installation commissioning and trial operation of electro mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE -I and II ( Rathkhola Bhimram, Kamola Jote Budhkaran) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. |  |  | ORD/000255/2023-2024 | 2161/SWSD | 29/11/2023 | 29/12/2023 | CHOWDHURY & BASU ENTERPRISE | 34.09 | 0 | 0 | 90
24 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Chhoto Maniram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Chhota Maniram Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000077/2022-2023 | 850/SWSD | 21/07/2022 | 04/10/2022 | UJJWAL ROY | 81.01 | 0 | 0 | 100
25 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000167/2022-2023 | 1327/SWSD | 14/09/2022 | 22/12/2022 | NORTH EAST CO-OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 46.37 | 0 | 0 | 100
26 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2022-2023 | 112/NMD | 03/02/2023 | 05/03/2023 | CHOWDHURY AND BASU ENTERPRISE | 32.88 | 0 | 0 | 100
27 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Bengaijote Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000265/2022-2023 | 2074/SWSD | 13/01/2023 | 08/04/2023 | KAMIRUL SK & CO | 91.79 | 0 | 0 | 100
28 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Balanced work of laying distribution system along with pump connection in connection with Augmentation of Naxalbari piped water supply scheme (chhota Maniram ZOne) under Naxalbari Block, Darjeeling District under siliguri Sub-division ,P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000239/2023-2024 | 523/SSD | 18/12/2023 | 18/01/2024 | UJJWAL ROY | 1.91 | 0 | 0 | 100
29 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Quotation Charges New service Connection at Naxalbari PWSS,TW-VI, Near Budhkaran under NMD,PHE Dte. Application No - 4003462594 Ref Id- 403258323 |  |  | BILL/00833/2024-2025 | BP/24-25/157 | 07/08/2024 | 07/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.34 | 0 | 0 | 0
30 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno programme at Budhkaran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Budhkaran Zone) within Naxalbari block, Darjeeling dist. under Siliguri Sub Division, PHE Dte. SL. NO. 16. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000141/2021-2022 | 2438/SWSD | 21/03/2022 | 31/01/2026 | DEBRAJ ENTERPRISE | 92.59 | 0 | 0 | 81
31 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Khalpara Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000076/2022-2023 | 849/SWSD | 21/07/2022 | 04/03/2026 | AKASH ENTERPRISE | 96.94 | 0 | 0 | 85
32 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) Kamala (Part) and Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kalibari Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 16. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000086/2022-2023 | 859/SWSD | 21/07/2022 | 11/07/2025 | PALLAB BHOWAL | 129.79 | 0 | 0 | 90
33 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Rathkhola Bhimram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 15. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000085/2022-2023 | 858/SWSD | 21/07/2022 | 11/03/2023 | M/S G.C. CONSTRUCTION & CO. | 90 | 0 | 0 | 50
34 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and providing functional household tap connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) & Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kotia Zone) under Naxalbari block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000137/2023-2024 | 1405/SWSD | 21/08/2023 | 16/03/2025 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 127.6 | 0 | 0 | 70
35 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Budhkraran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Roypara Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 17. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000005/2022-2023 | 37/SWSD | 07/04/2022 | 01/01/2026 | SUBIR CH. CHOWDHURY | 138.01 | 0 | 0 | 100
Total | [13 empty] | 1606.51 | 0 | 0