## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 2041/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 111.41 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Sinking of 01(one) No Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd Tube well site for Augmentation of Dumriguri Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000252/2022-2023 | 2166/SWSD | 30/12/2022 | 09/01/2023 | M/S K. R. S. CONSTRUCTION | 8.14 | 6.47 | 79.53 | 100
3 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Repairing Of Damaged Pipe Line alongwith House Connections at Airport More Sansad, Lokhnath nagar, Bhujiyapani under Dumriguri Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2023-2024 | 962/SWSD | 24/07/2023 | 08/08/2023 | U.K CONSTRUCTIONS | 4.47 | 4.19 | 93.57 | 100
4 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1459/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 19.64 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | New Service Connection Charge for DUMRIGURI, TW No. I, (REJU) BAGDOGRA CCC [APPLICATION NO.4003151289 , Reference ID : 403013234] |  |  | BILL/00250/2023-2024 | BP/23-24/28 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000661/2023-2024 | 1475/NMD | 17/08/2023 | 16/09/2023 | RAJEEV RANJAN OJHA | 23 | 14.05 | 61.09 | 30
7 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Infrastructure Cost for DUMRIGURI (REJU) , under BAGDOGRA CCC , [APPLICATION NO. 100000094733, Reference ID : 860287023] |  |  | BILL/02024/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.72 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Work Order for Repairing of 350 Cu.M. R.C.C Elevated Reservoir, 20 mtrs. Staging Height at the Head Work Site, Laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), Construction of one number pump house (3.00 X 3.60m), Sinking of 01 (one) no tubewell (ODEX-165 method) and Boundary wall for Dumriguri PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri Water Supply Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000198/2023-2024 | 1978/SWSD | 26/10/2023 | 01/12/2025 | DRISHTI CONSTRUCTION | 529.56 | 59.66 | 11.27 | 80
9 | DARJEELING |  | Central Drilling | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 0 | 10
10 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | Augmentation | Acceptance cum Work Order for Additional Work (F.H.T.C , Paverblock Pavement etc ), under JJM/Jal Swapna in connection with rejuvenation of DAMDAMA PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000006/2025-2026 | 1233/SWSD | 24/04/2025 | 08/06/2025 | KAMAL GHOSH | 4.73 | 0 | 0 | 0
Total | [13 empty] | 1176.11 | 84.37 | 7.17