## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 2024/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 17.86 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000084/2022-2023 | 857/SWSD | 21/07/2022 | 20/08/2022 | TUSHAR KANTI SEAL | 29.64 | 0 | 0 | 90
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 29/10/2022 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000813/2020-2021 | 308/SSD | 13/08/2020 | 13/08/2020 | SUDIP BASAK | 0.88 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1467/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 20.24 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Continuation order for hiring of 1 (one) no. Maxi Cab with engine capacity less than or Equal to 2000 CC (with Air Condition) for the office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022 (for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte.) |  |  | BILL/00052/2022-2023 | BP-2022-23-118 | 20/02/2023 | 20/02/2023 | HIMADRI DAM | 1.45 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | New Service Connection Charge for CHOTO DILSARAMJOTE W/S Scheme, T/W No. III, Zone-II under UTTAR RAMDHAN CCC, [APPLICATION NO. 4003055461, Reference ID : 402933290] |  |  | BILL/00048/2022-2023 | BP/22-23/137 | 01/03/2023 | 01/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.54 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | New Service Connection Charge for UTTAR RAMDHAN, ZONE-I,T/W -I, under NAXALBARI CCC, [APPLICATION NO. 4003079475, Reference ID : 402958536] |  |  | BILL/00583/2022-2023 | BP/22-23/137 | 01/03/2023 | 01/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000083/2022-2023 | 856/SWSD | 21/07/2022 | 29/10/2022 | PALLAB BHOWAL | 162.34 | 0 | 0 | 30
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR RAMDHAN WATER SUPPLY SCHEME, (ZONE-I) TW No. I AND II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2022-2023 | 106/NMD | 03/02/2023 | 05/03/2023 | S.P. ENTERPRISE | 32.98 | 0 | 0 | 50
Total | [13 empty] | 312.91 | 0 | 0