## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 2023/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 52.56 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 11/01/2023 | G. TECH INDIA | 3.21 | 0 | 0 | 100
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 1457/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 2.35 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Temporary hiring 01 (one) nos. maxi cab with driver for official screening cum enquiry at Kalimpong in favour of Deputy Superintending Engineer, North Bengal Circle-I PHE Dte.& his team |  |  | BILL/00201/2023-2024 | BP-2023-24-64 | 28/09/2023 | 28/09/2023 | SUDIP BASAK | 0.07 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Construction of rig bore big dia deep tube well 4 (four) nos. by ODEX-165 method of drilling of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000036/2023-2024 | 648/SWSD | 15/06/2023 | 15/07/2023 | BUDDHADEV NAG | 30.05 | 0 | 0 | 75
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, under PHANSIDEWA CCC [APPLICATION NO. 4003289610 ; Reference ID : 403124950] |  |  | BILL/01672/2023-2024 | BP/23-24/200 | 27/12/2023 | 27/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, T/W No. III, under PHANSIDEWAI CCC [APPLICATION NO.4003294308 ; Reference ID : 403128805] |  |  | BILL/01783/2023-2024 | BP/23-24/218 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.3 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO.4003298928 ; Reference ID : 403128850] |  |  | BILL/01784/2023-2024 | BP/23-24/219 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Construction of Pump House (4 Nos.) (5.4 X 3.60) size with (1.35 X 2.10 m) size with toilet. Plinth protection etc. installation of IEP and boundary wall at Zone-II, Zone-III, Zone-IV & Zone-V of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000034/2023-2024 | 647/SWSD | 15/06/2023 | 01/04/2026 | BUDDHADEV NAG | 91.93 | 0 | 0 | 30
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Construction of 250 cu.m. capacity R.C.C. Overhead Reservoir, 20 mtrs. Staging height including laying distribution system and allied with providing functional household tap connection (FHTC) at distribution pipeline of BANDARGACHH and adjoining mouza's water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. A. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2022-2023 | 817/SWSD | 19/07/2022 | 01/03/2026 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 441.79 | 0 | 0 | 25
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Acceptance cum Work Order for Additional Laying distribution system for (Z-V) allied with functional house hold tap connection (FHTC) at Augmentation of Bandargachh and Adjoining Mouzas Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000017/2025-2026 | 1243/SWSD | 24/04/2025 | 08/06/2025 | SHRI ANNAPURNA DISTRIBUTORS | 48.42 | 0 | 0 | 0
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2023-2024 | 1752/NMD | 31/10/2023 | 13/04/2025 | SUBODH KUMAR BANIK | 32.74 | 0 | 0 | 100
Total | [13 empty] | 724.61 | 0 | 0