## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 2060/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 65.06 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 11/01/2023 | G. TECH INDIA | 3.21 | 1.21 | 37.6 | 100
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | FURTHER ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2023 TO 31.08.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. 6 (SIX) MONTHS. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000336/2022-2023 | 2642/SWSD | 01/03/2023 | 01/09/2023 | HIMADRI DAM | 0.88 | 1.6 | 181.97 | 100
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1458/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 6.05 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON, T/W No. I, ZONE-I, under PHANSIDEWA CCC [APPLICATION NO. 4003305873 ; Reference ID : 403135372] |  |  | BILL/01815/2023-2024 | BP/23-24/275 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.96 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON , T/W No. II , ZONE-I, under PHANSIDAWA CCC, [APPLICATION NO. 4003317696, Reference ID : 403145882] |  |  | BILL/01941/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.53 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON , T/W No. I , ZONE-II, under PHANSIDAWA CCC, [APPLICATION NO. 4003317715, Reference ID : 403145870] |  |  | BILL/01940/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | Construction of 150 cu.m. Overhead reservoir, 2 nos. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation of MADHYA BANSGAON (Zone-I) Piped Water Supply Scheme and Construction of 350 cu.m. overhead reservoir, 1 no. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation work of MADHYA BANSGAON (Zone-II) Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000104/2023-2024 | 1130/SWSD | 07/08/2023 | 01/12/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 869.38 | 363.38 | 41.8 | 19
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II and (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000788/2023-2024 | 1652/NMD | 29/09/2023 | 31/08/2025 | M/S SWAPAN BANERJEE | 22.53 | 4.64 | 20.58 | 100
10 | DARJEELING |  | Central Drilling | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22339.21 | 370.82 | 1.66