## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING | SM/10824 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1460/SWSD | 29/09/2022 |  | Resource Division | 4.89 | 0 | 0 | 0
2 | DARJEELING | Phansidewa | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING | SM/10824 | New | IMPLEMENTATION OF MINI PIPED WATER SUPPLY SCHEME IN 32 (THIRTY TWO) NOS. VILLAGES UNDER DIFFERENT BLOCKS HAVING LESS THAN 100 (ONE HUNDRED) HOUSEHOLDS UNDER DARJEELING DISTRICT IN CONNECTION WITH JAL SWAPNA. SL. NO. 1. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer (Mechanical),Junior Engineer(Civil) | ORD/000150/2022-2023 | 753/SWSD | 08/07/2022 | 06/09/2022 | ROY ENGINEERS | 1188.6 | 25.48 | 2.14 | 80
Total | [13 empty] | 1193.49 | 25.48 | 2.13