## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dakhshin Bagdogra Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000156/2022-2023 | 278/SSD | 25/05/2022 | 14/06/2022 | SUBHANKAR GHOSH | 3.09 | 3.06 | 99.03 | 100
2 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1462/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 7.47 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 2054/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 65.62 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Central Drilling | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Construction of 200 cu.m. Capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of pump house (5.40 X 3.6 m) and pump house (3.60 X 3.00 m) with sanitary and plumbing arrangement, iron elimination plant (IEP) with blower room and soil investingation at head work site for DAKSHIN BAGDOGRA PWSS, Block Naxalbari Dist. Darjeeling under Siliguri W/S Division, PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000125/2023-2024 | 1200/SWSD | 10/08/2023 | 02/04/2026 | NETWAY SOLUTION | 332.54 | 0 | 0 | 30
6 | DARJEELING | Naxalbari | Northern Mechanical | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Quotation for new service connection at T.W No-I of DAKSHIN BAGDOGRA PWSS in the dist. Darjeeling |  |  | BILL/00293/2024-2025 | BP/24-25/36 | 14/05/2024 | 14/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.06 | 0 | 0 | 0
7 | DARJEELING | Naxalbari | Northern Mechanical | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at DAKSHIN BAGDOGRA PWSS for T/W No. II in the district of Darjeeling under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000845/2024-2025 | 583/NMD | 07/02/2025 | 09/03/2025 | SAIKAT SINHA | 12.1 | 0 | 0 | 0
8 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Payment for Survey and Demarcation of 0.0224Ha Forest Land Divesion to the WEST STATE FOREST DEVELOPMENT AGENCY FOR In -principal (Stage-I) approval of Central Government under Section 2(1)ii of the Van (Sanrakshan Evam Samvardhan) Adhiniyam,1980 for non forestry use of 0.0224 Ha of Forest Land in favour of West Bengal Public Health Engineering Directorate for Gravity Based Water Supply Scheme at Dakshin Bagdogra PWSS,Upper Bagdogra GP,Naxalbari under Kurseong Forest Division in Darjeeling District of West Bengal (Proposal No.FP/WB/WATER/514521/2024 Dated-22.072025.) |  |  | BILL/00453/2025-2026 |  | 28/11/2025 | 28/11/2025 | WEST BENGAL STATE FOREST DEVELOPMENT AGENCY | 0.62 | 0 | 0 | 0
9 | DARJEELING | Naxalbari | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | New | Payment for Net Present Value(NPV) and Compensatory Afforestation (CA) for theIn principal stage (Stage-I) approval of Central Government under Section 2(1 (ii) of the Van (Sankrakshan Evam Samvardhan) Adhiniyam 1980 for non forestry use of 0.224 ha of forest land in favour of West Bengal Public Health Engineering Directorate for Gravity Based Water Supply Scheme of Dakshin Bagdogra PWSS,Upper Bagdogra GP,Naxalbari under Kurseong Forest Division in Darjeeling District of West Bengal (Proposal No.FP/WB/WATER/514521/2024 Dated-22.07.2025) |  |  | BILL/00452/2025-2026 |  | 28/11/2025 | 28/11/2025 | CAMPA WESTBENGAL | 2.56 | 0 | 0 | 0
Total | [13 empty] | 21773.82 | 3.06 | 0.01