## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Gharia Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) |  | ORD/000160/2022-2023 | 298/SSD | 01/06/2022 | 21/06/2022 | SUBHANKAR GHOSH | 3.03 | 0 | 0 | 100
2 | DARJEELING | Matigara | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Work order construction of 200 cu.m capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site, laying rising main, laying distribution pipe line with functional household tap connection (FHTC), construction of pump house (5.40 X 3.60m) and pump house (3.60 X 3.00m) without sanitary and plumbing arrangement, iron elemination plant (IEP) with blower room and soil investigation at H/W site for Bara Gharia PWSS, block Matigara, Dist - Darjeeling under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000180/2023-2024 | 1731/SWSD | 21/09/2023 | 03/05/2024 | CAPITAL ENGINEERS | 338.72 | 0 | 0 | 0
3 | DARJEELING | Matigara | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1376/SWD | 21/09/2022 | 21/09/2022 | Resource Division | 6.69 | 0 | 0 | 0
4 | DARJEELING | Matigara | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 2055/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 54.77 | 0 | 0 | 0
5 | DARJEELING | Matigara | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 2289/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 5 | 0 | 0 | 0
6 | DARJEELING | Matigara | Northern Mechanical | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PIPED WATER SUPLY SCHEME, TW No.- I AND II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2023-2024 | 1656/NMD | 29/09/2023 | 29/10/2023 | M/S PARITOSH BHOWMICK AND CO. | 11.49 | 0 | 0 | 50
7 | DARJEELING | Matigara | Central Drilling | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21759.46 | 0 | 0