## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed M.M TERAI Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. |  | Junior Engineer(Civil) | ORD/000153/2022-2023 | 272/SSD | 20/05/2022 | 09/06/2022 | SUBHANKAR GHOSH | 2.35 | 2.35 | 100 | 100
2 | DARJEELING | Naxalbari | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | New | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 2026/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 1.45 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | New | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1464/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 2.16 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | New | Construction of Pump House (5.4 X 3.65) size, Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling, boundary wall allied with laying of rising main, distribution system and providing functional household tap connection (FHTC) under JJM for M.M. TERAI PIPED WATER SUPPLY SCHEME within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000245/2022-2023 | 2094/SWSD | 22/12/2022 | 07/03/2023 | SUDIP BASAK | 88.33 | 11.38 | 12.88 | 60
5 | DARJEELING | Naxalbari | Northern Mechanical | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | New | New Service Connection Charge for M.M TERAI, T/W No. I under NAXALBARI CCC [APPLICATION NO. 4003312828 ; Reference ID : 403142027] |  |  | BILL/01919/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.57 | 0 | 0 | 0
Total | [13 empty] | 105.85 | 13.72 | 12.97