## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Rupsing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000152/2022-2023 | 268/SSD | 20/05/2022 | 09/06/2022 | SUBHANKAR GHOSH | 2.73 | 0 | 0 | 100
2 | DARJEELING | Naxalbari | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 2053/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 45.28 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1463/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 6.38 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Northern Mechanical | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RUPSING PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000800/2023-2024 | 1657/NMD | 29/09/2023 | 29/10/2023 | TALUKDER ENTERPRISE | 11.5 | 0 | 0 | 50
5 | DARJEELING | Naxalbari | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head work site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of one number pump house (5.40 X 3.60 m), one number pump house (3.00 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of two (2) nos. tube well (ODEX-165 method), soil investigation at HW site and boundary wall for Rupsing PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri W/S Division, PHE Dte. |  |  | ORD/000253/2023-2024 | 84/SWSD | 10/01/2024 | 06/09/2024 | YAMA CONSTRUCTIONS LLP | 255.16 | 0 | 0 | 0
6 | DARJEELING | Naxalbari | Central Drilling | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21660.8 | 0 | 0