## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bansgaon Mangachh Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000151/2022-2023 | 267/SSD | 20/05/2022 | 09/06/2022 | SUBHANKAR GHOSH | 2.23 | 2.23 | 100 | 100
2 | DARJEELING | Phansidewa | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1951/SWSD | 07/12/2022 | 07/12/2022 | Resource Division | 2.58 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Laying distribution system allied with functional house hold tap connection (FHTC) including boring of new tube well and Iron elimination plant under JJM at BANSGAON MANGACHH and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000278/2022-2023 | 2656/SWSD | 02/03/2023 | 15/06/2023 | CUBES 'N' PYRAMIDS | 119.4 | 7.7 | 6.45 | 10
4 | DARJEELING | Phansidewa | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1466/SWSD | 29/09/2022 | 29/09/2022 | Resource Division | 1.33 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | New Service Connection Charge for BANSGAON MANGACHH, T.W. No. I under PHANSIDEWA CCC, [APPLICATION NO. 4003194676, Reference ID : 403046883] |  |  | BILL/00598/2023-2024 | BP/23-24/75 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.07 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Additional Charges For New service connection At BANSHGAON MANGACHH Water Supply scheme Under NMD, PHE Dte. Application No -4003194676 Ref ID- 403046883 |  |  | BILL/00374/2024-2025 | BP/24-25/78 | 06/06/2024 | 06/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 1376/NMD | 09/08/2023 | 01/10/2025 | M/S DILIP MITRA | 10.61 | 0 | 0 | 90
8 | DARJEELING | Phansidewa | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | New | Addl. quotation in connection with Bansgaon Mangachh water supply scheme under NMD Phe dte. Ref ID-860321318 Application ID- 100000126288 |  |  | BILL/02227/2024-2025 | BP/24-25/252 | 17/03/2025 | 17/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
Total | [13 empty] | 147.39 | 9.92 | 6.73