## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Adalpur Dwitiyo Khanda Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) |  | ORD/000158/2022-2023 | 288/SSD | 26/05/2022 | 15/06/2022 | SUBHANKAR GHOSH | 2.82 | 2.81 | 99.36 | 100
2 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 2051/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 31.66 | 0 | 0 | 0
3 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1375/SWSD | 21/09/2022 | 21/09/2022 | Resource Division | 10.86 | 0 | 0 | 0
4 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 2288/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 3.57 | 0 | 0 | 0
5 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 16/03/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 2.86 | 13.24 | 50
6 | DARJEELING | Matigara | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | New Service Connection Charge for BARAADALPUR, T/W No. I, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299617 ; Reference ID : 403130073] |  |  | BILL/01820/2023-2024 | BP/23-24/280 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
7 | DARJEELING | Matigara | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. II, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300577 ; Reference ID : 403130594] |  |  | BILL/01738/2023-2024 | BP/23-24/221 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0 | 0
8 | DARJEELING | Matigara | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. I, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300574 ; Reference ID : 403130566] |  |  | BILL/01737/2023-2024 | BP/23-24/220 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.47 | 0 | 0 | 0
9 | DARJEELING | Matigara | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | New Service Connection Charge for BARAADALPUR, T/W No. II, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299635 ; Reference ID : 403130072] |  |  | BILL/01817/2023-2024 | BP/23-24/277 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.16 | 0 | 0 | 0
10 | DARJEELING | Matigara | Central Drilling | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 9.37 | 0.04 | 11
11 | DARJEELING | Matigara | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Construction of 200 Cu.M & 150 cum capacity RCC Elevated Reservoir each of 20 mtrs Staging Height at the head works sites,laying rising main,Laying distribution pipeline with Functional Household Tap Connection (FHTC), construction of Two number pump houses(5.40 X 3.60 m),Two number pump houses (3.00 X 3.60 m), Iron Elimination Plant (IEP) with Blower room ,Sinking of four (4) nos Tube well (ODEX-165 method),Soil Investigation at H/W sites and Boundary wall for BARA ADALPUR DWITYA KHANDA PWSS (ZONE I & II) Block:Matigara,Dist: Darjeeling under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000109/2023-2024 | 1150/SWSD | 08/08/2023 | 29/09/2025 | MAHADEO PRASAD AGARWAL & CO | 510.38 | 221.38 | 43.38 | 80
12 | DARJEELING | Matigara | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 1579/NMD | 08/09/2023 | 02/08/2025 | CHOWDHURY AND BASU ENTERPRISE | 23.46 | 19.51 | 83.17 | 100
Total | [13 empty] | 21973.98 | 255.92 | 1.16