## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 2032/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 1.97 | 0 | 0 | 0
2 | DARJEELING |  | Central Drilling | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 6.85 | 10.12 | 10
3 | DARJEELING |  | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Quotation Charges New service Connection at Purba Madati PWSS under NMD,PHE Dte. Application No - 4003339413 Ref Id- 403162854 |  |  | BILL/00835/2024-2025 | BP/24-25/157 | 07/08/2024 | 07/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Charges for New Service connection at Purba Madati PWSS,TW No- II under NMD , PHEW Dte. Application No- 4003498842 Ref ID- 403286657 |  |  | BILL/01403/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.19 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000665/2023-2024 | 1479/NMD | 17/08/2023 | 30/10/2025 | RIPON DAS | 23.26 | 0 | 0 | 90
6 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | Augmentation | Construction of 2 (two) Nos. Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size toilet, Rig bore 2 (two) Nos. big dia deep T/W by Odex-165 method of drilliig, boundary wall at 2 (two) sites. laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum/hr. at SATHBIL PASCHIM MADATI Mouza and 20 cu.m./hr opposite of MADATI HIGH SCHOOL) required platform and drain etc. for Rejuvenation at PURBA MADATI Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000133/2023-2024 | 1372/SWSD | 18/08/2023 | 23/03/2026 | M/S G.C. CONSTRUCTION & CO. | 117.74 | 5.82 | 4.95 | 35
Total | [13 empty] | 221.81 | 12.67 | 5.71