## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 2030/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 0.98 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2023-2024 | 1477/NMD | 17/08/2023 | 16/09/2023 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 12.44 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 2234/SWSD | 06/01/2023 | 06/01/2023 | Resource Division | 0.98 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | Acceptance cum work order for Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia Deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and Supplying, Fabrication, Erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (20 cu.m./hour) required platform and drain etc. for Rejuvenation of Dangarvita Piped Water Supply Scheme at Kharibari block under under Siliguri Sub Division.P.H.E.Dte.in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000182/2024-2025 | 3025/SWSD | 13/11/2024 | 11/02/2025 | BUDDHADEV NAG | 66.21 | 0 | 0 | 0
5 | DARJEELING |  | Central Drilling | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 6.54 | 9.66 | 10
6 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | Augmentation | New Service Connection Charge for DANGARVITA, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003321689, Reference ID : 403147924] |  |  | BILL/01943/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.46 | 0 | 0 | 0
Total | [13 empty] | 151.77 | 6.54 | 4.31