## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2031/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 0.98 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 529/NMD | 10/05/2023 | 09/06/2023 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 11.64 | 11.1 | 95.35 | 90
3 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | Augmentation | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum./hr) required platform and drain etc. for rejuvenation of Paschim Madati Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, PHE Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000268/2022-2023 | 2366/SWSD | 24/01/2023 | 02/04/2025 | AKASH ENTERPRISE | 67.76 | 52.59 | 77.62 | 100
4 | DARJEELING |  | Northern Mechanical | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | Augmentation | New Service Connection Charge for Rejuvenation of Paschim Madati, TW No. I, BIDHANNAGAR CCC, [APPLICATION NO. 4003143720, Reference ID : 803008623] |  |  | BILL/00031/2023-2024 | BP/23-24/08 | 16/05/2023 | 16/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | Augmentation | Acceptance cum Work Order for Improvement of Existing FHTC with existing pipelines for Rejuvenation of Paschim Madati PWSS under Jal Jeeban Mission (JJM) at Phansidewa Block within Siliguri Sub- Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000015/2025-2026 | 1241/SWSD | 24/04/2025 | 24/05/2025 | AKASH ENTERPRISE | 16.03 | 0 | 0 | 0
Total | [13 empty] | 97.2 | 63.69 | 65.53