## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Laying distribution system along with boring of new tubewell, construction of pump house, boundary wall and providing FHTC at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under JJM/Jal Swapna in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri Sub Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000246/2022-2023 | 2095/SWSD | 22/12/2022 | 02/03/2026 | KAMAL GHOSH | 53.81 | 53.08 | 98.65 | 98
2 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 2028/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 0.98 | 0 | 0 | 0
3 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000799/2022-2023 | 164/NMD | 17/02/2023 | 19/03/2023 | MAA BHABOTARINE ENTERPRISE | 10.76 | 7.47 | 69.37 | 70
4 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | New Service Connection Charge for rrjuvenation of Dhulia PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144973 ; Reference ID : 403013028] |  |  | BILL/00040/2023-2024 | BP/23-24/11 | 16/05/2023 | 16/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under Jal Jeevan Mission in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri W/S Division, PHD Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000142/2024-2025 | 2536/SWSD | 18/09/2024 | 02/02/2025 | KAMAL GHOSH | 7.7 | 0 | 0 | 80
6 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Acceptance cum Work Order for IMPROVEMENT OF EXISTING PIPELINE & FHTC DUE TO ROAD & DRAIN CONSTRUCTION at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under JJM/Jal Swapna in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri Sub Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000010/2025-2026 | 1236/SWSD | 24/04/2025 | 24/05/2025 | KAMAL GHOSH | 16.83 | 0 | 0 | 0
Total | [13 empty] | 90.81 | 60.55 | 66.67