## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 2028/SWSD | 16/12/2022 |  | Resource Division | 0.98 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | New Service Connection Charge for rrjuvenation of Dhulia PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144973 ; Reference ID : 403013028] |  |  | BILL/00040/2023-2024 | BP/23-24/11 | 16/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
3 | DARJEELING |  | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000799/2022-2023 | 164/NMD | 17/02/2023 | 19/03/2023 | MAA BHABOTARINE ENTERPRISE | 10.76 | 7.47 | 69.37 | 70
4 | DARJEELING |  | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | Augmentation | Laying distribution system along with boring of new tubewell, construction of pump house, boundary wall and providing FHTC at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under JJM/Jal Swapna in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri Sub Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000246/2022-2023 | 2095/SWSD | 22/12/2022 | 07/03/2023 | KAMAL GHOSH | 53.81 | 19.36 | 35.98 | 98
Total | [13 empty] | 66.28 | 26.83 | 40.47