## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1949/SWSD | 07/12/2022 | 07/12/2022 | Resource Division | 11.72 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Continuation order for Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000353/2022-2023 | 1834/SWSD | 25/11/2022 | 26/05/2023 | SUDIP BASAK | 0.89 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Acceptance cum Work order Construction of boundary wall at head work site allied with Functional Household Tap Connection (FHTC) for Augmentation Trihana Tea Garden Area PWSS under Naxalbari Block under Siliguri Water Supply Division ,P.H.E,Dte.. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000177/2023-2024 | 1690/SWSD | 19/09/2023 | 03/11/2023 | S.K. BANIK | 30.58 | 11.78 | 38.52 | 40
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000055/2023-2024 | 248/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.5 | 2.5 | 100 | 100
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | New Service Connection Charge for TRIHANA TEA GARDEN, under NAXALBARI CCC, [APPLICATION NO. 4003079478, Reference ID : 402958535] |  |  | BILL/00582/2022-2023 | BP/22-23/145 | 04/03/2023 | 04/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | New Service Connection Charge for TRIHANA W/S SCHEME, T/W II, under NAXALBARI CCC, [APPLICATION NO. 4003210228, Reference ID : 403058760] |  |  | BILL/01163/2023-2024 | BP/23-24/142 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.75 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Sinking of 02(Two) Nos. Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at Tube Well Sites for Augmentation of TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000236/2022-2023 | 2092/SWSD | 22/12/2022 | 16/01/2023 | SUBHADEEP ENTERPRISE | 16.28 | 16.28 | 100 | 100
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Construction of 2 Nos. Pump House (5.4 X 3.60) size, boundary wall allied with laying of rising main, distribution system & providing functional household tap connection (FHTC) for Augmentation TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000202/2022-2023 | 1675/SWSD | 10/11/2022 | 24/01/2023 | S.K. BANIK | 94.26 | 72.11 | 76.51 | 80
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Supplementary work for supply & delivery of column pipe & cable for AUGMENTATION OF TRIHANA TEA GARDEN,TW-I in the dist of Darjeeling under Northern Mechanical Division., PHE Dte. |  | Junior Engineer | ORD/001029/2023-2024 | 366/SMSD | 06/12/2023 | 16/12/2023 | MAA ENTERPRISES | 1.23 | 1.23 | 100 | 100
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Supply & delivery of Column pipe under JJM project at Trihana Tea Garden PWSS in the dist of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001038/2023-2024 | 421/SMSD | 19/12/2023 | 29/12/2023 | B.B. CONCERNED | 0.94 | 0.94 | 100 | 100
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000794/2022-2023 | 108/NMD | 03/02/2023 | 05/03/2023 | MAA ENTERPRISES | 11.55 | 8.67 | 75.05 | 80
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000998/2024-2025 | 17/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0 | 0
13 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 05/02/2025 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
15 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2023-2024 | 1753/NMD | 31/10/2023 | 02/02/2025 | SUBODH KUMAR BANIK | 11.07 | 8.29 | 74.88 | 100
Total | [13 empty] | 303.63 | 121.8 | 40.11