## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 2033/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 15.89 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000054/2023-2024 | 247/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.53 | 0 | 0 | 100
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000664/2023-2024 | 1478/NMD | 17/08/2023 | 16/09/2023 | SAIKAT SINHA | 12.5 | 0 | 0 | 100
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | New Service Connection Charge for ORD TERAI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003291503 ; Reference ID : 403124697] |  |  | BILL/01746/2023-2024 | BP/23-24/222 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.07 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | New Service Connection Charge for ORD TERAI, T/W No. II under NAXALBARI CCC [APPLICATION NO. 4003312826 , Reference ID : 4031141988] |  |  | BILL/01918/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000998/2024-2025 | 17/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 05/02/2025 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | Augmentation | Construction of 200 cum capacity RCC Elevated Reservoir, 20 mtrs. Staging height at the head works site along with distribution system rising main, iron elimination plant, pump houses, boundary walls, functional house hold tap connection (FHTC), soil investigation and other allied works under Jal Jeevan Mission (JJM) for Augmentation of ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000277/2022-2023 | 2655/SWSD | 02/03/2023 | 20/06/2025 | VIJAY KUMAR ARORA | 209.89 | 0 | 0 | 65
Total | [13 empty] | 369.15 | 0 | 0