## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Hetmuri Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil) | ORD/000157/2022-2023 | 287/SSD | 26/05/2022 | 15/06/2022 | SUBHANKAR GHOSH | 3.54 | 0 | 0 | 100
2 | DARJEELING | Phansidewa | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 2056/swsd | 16/12/2022 | 16/12/2022 | Resource Division | 23.32 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Construction of 200 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Main construction of 4 nos big dia rig bore tube well by ODEX - 165, Pump House (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plant , Boundary Wall including Functional Household Tap Connection at HETMURI Piped Water Supply Scheme (ZONE I , II & III) under Phansidewa Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000116/2023-2024 | 1212/SWSD | 11/08/2023 | 25/12/2025 | K.R.ENTERPRISE | 577.26 | 0 | 0 | 10
4 | DARJEELING | Phansidewa | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HETMURI PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II, (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000746/2023-2024 | 1576/NMD | 08/09/2023 | 08/10/2023 | ALPHA ENTERPRISE | 31.45 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Central Drilling | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
6 | DARJEELING | Phansidewa | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 75/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 11.05 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | New Service Connection Charge for HETMURII, T/W No. I, under PHANSIDEWAI CCC [APPLICATION NO. 4003293269 , Reference ID : 403129587] |  |  | BILL/01781/2023-2024 | BP/23-24/259 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.57 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | New service connection at Hetmuri Z-II ,TW-II under NMD, PHE dte. Application No- 4003425299 Ref. Id- 403230924 |  |  | BILL/00417/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.45 | 0 | 0 | 0
9 | DARJEELING | Phansidewa | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | New Service Connection Charge for HETMURII, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO. 4003293284 , Reference ID : 403129595] |  |  | BILL/01782/2023-2024 | BP/23-24/258 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5 | 0 | 0 | 0
10 | DARJEELING | Phansidewa | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | New service connection at Hetmuri Z-II ,TW-I under NMD, PHE dte. Application No- 4003425334 Ref. Id- 403230933 |  |  | BILL/00418/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.63 | 0 | 0 | 0
11 | DARJEELING | Phansidewa | Central Drilling | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22083.72 | 0 | 0