## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Mohorgaon Tea Garden Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil) | ORD/000159/2022-2023 | 289/SSD | 26/05/2022 | 15/06/2022 | SUBHANKAR GHOSH | 3.3 | 3.28 | 99.18 | 100
2 | DARJEELING | Matigara | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 2050/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 24.61 | 0 | 0 | 0
3 | DARJEELING | Matigara | Central Drilling | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | DARJEELING | Matigara | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,IIand (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000787/2023-2024 | 1651/NMD | 29/09/2023 | 29/10/2023 | M/S SAJAHAN CHOWDHURY | 23.8 | 18.69 | 78.53 | 100
5 | DARJEELING | Matigara | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Work Order for Construction of 200 cu.m capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main, Construction of 3 nos Big dia rig bore tube well by ODEX 165, Pump House (5.4 X 3.60 m), Iron Elemination Plant, Boundary Wall including Functional Household Tap Connection at MOHORGAON TEA GARDEN Piped Water Supply Scheme (Zone I & II) under Matigara Block, Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000197/2023-2024 | 1977/SWSD | 26/10/2023 | 29/03/2026 | EASHAN POLYMERS PRIVATE LIMITED | 492.88 | 140.49 | 28.5 | 35
6 | DARJEELING | Matigara | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 2303/SWSD | 12/12/2023 | 12/12/2023 | Resource Division | 2.72 | 0 | 0 | 0
7 | DARJEELING | Matigara | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 62/SWSD | 09/01/2024 | 09/01/2024 | Resource Division | 6.3 | 0 | 0 | 0
8 | DARJEELING | Matigara | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No.II, under MATIGARA CCC, [APPLICATION NO. 4003316001, Reference ID : 403143726] |  |  | BILL/01944/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.06 | 0 | 0 | 0
9 | DARJEELING | Matigara | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | Infrastructure Cost for MOHORGAON T/W-III, under PRADHAN NAGAR CCC , [APPLICATION NO. 4003337401, Reference ID : 403161193] |  |  | BILL/02025/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0 | 0
10 | DARJEELING | Matigara | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | New | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No. I, under MATIGARA CCC, [APPLICATION NO. 4003315986, Reference ID : 403143724] |  |  | BILL/01945/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.4 | 0 | 0 | 0
Total | [13 empty] | 21920.87 | 162.45 | 0.74