## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 2057/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 45.97 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000050/2023-2024 | 243/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.34 | 0 | 0 | 100
3 | DARJEELING |  | Central Drilling | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000030/2024-2025 | 560/CDD | 06/08/2024 | 06/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 10
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Laying distribution of pipeline, construction of boundary wall, pump house, installation of I.E.Plant ,Providing functional House hold Tap Connection (FHTC) at ( Zone -I) , ( Zone-II ) & ( Zone-III ) for augmentation of Mangalsing PWSS under JJM within Naxalbari block under Siliguri WS Division, PHE Dte. Sl No. 09 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000077/2023-2024 | 868/SWSD | 14/07/2023 | 10/01/2024 | M/S DOLPHIN CONSTRUCTION CO | 396.62 | 0 | 0 | 40
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , (Zone-III) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2023-2024 | 1384/NMD | 09/08/2023 | 08/09/2023 | BONANZA ENTERPRISE | 12.99 | 0 | 0 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Laying New HDPE Pipe Line Under Mangalsingh Pwss From Second Tubewell Site To Sebdullhajote Mouza ( Kanu Sanyal Basti) , Under Siliguri Sub Division, Under Siliguri W/S Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000189/2023-2024 | 1949/SWSD | 16/10/2023 | 31/10/2023 | NARAYAN CH GHOSH | 7.12 | 0 | 0 | 95
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Shifting of existing pipeline to new pipeline ,house connection along with laying of additional pipeline at Sebdella Mouza and Mangalsingh Mouza under Mangalsingh Water supply scheme under Siliguri w/s Division, PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000141/2024-2025 | 2535/SWSD | 18/09/2024 | 18/10/2024 | NARAYAN CH GHOSH | 4.92 | 0 | 0 | 100
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | New Service Connection Charge for MANGALSING, T/W No. I,ZONE-II under NAXALBARI CCC [APPLICATION NO. 4003289754 ; Reference ID : 403122959] |  |  | BILL/01708/2023-2024 |  | 22/12/2023 | 22/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 05/02/2025 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | Augmentation | Acceptance cum work order for Repair and Renovation of Boundary wall( Zn-II ) ,Approach road & Drain (Zn-III) , Boosting Pump Connection(Zn-I) and allied works for the Augmentation of Mangalsing Piped Water Supply Scheme in connection with JJM under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000009/2025-2026 | 1235/SWSD | 24/04/2025 | 08/06/2025 | NARAYAN CH GHOSH | 8.25 | 0 | 0 | 0
Total | [13 empty] | 504.08 | 0 | 0