## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 2058/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 23.57 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , (Zone-II) TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1377/NMD | 09/08/2023 | 08/09/2023 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 10.6 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000049/2023-2024 | 242/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.19 | 0 | 0 | 100
4 | DARJEELING |  | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000031/2024-2025 | 563/CDD | 07/08/2024 | 07/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Renovation of the pump House and Others allied Works at Mandalaguri (H/W) site of Mandalaguri Piped Water Supply Scheme under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000144/2024-2025 | 2538/SWSD | 18/09/2024 | 02/11/2024 | K.K.GHOSH & CO. | 3.2 | 0 | 0 | 0
6 | DARJEELING |  | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | New Service Connection Charge for MANDALAGURI, T/W-I, under MATIGARA CCC, [APPLICATION NO. 4003340645, Reference ID : 403163196] |  |  | BILL/02138/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.1 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Installation of two tank chlorination system at MANDALAGURI and other adjacent water supply scheme UNDER JJM under MATIGARA Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. |  | Junior Engineer | ORD/000889/2024-2025 | 81/SMSD | 07/02/2025 | 17/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 1.1 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 05/02/2025 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
Total | [13 empty] | 141.8 | 0 | 0