## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 2058/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 23.57 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , (Zone-II) TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1377/NMD | 09/08/2023 | 08/09/2023 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 10.6 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000049/2023-2024 | 242/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.19 | 0 | 0 | 100
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Construction of 250 cum Over Head Reservoir, Laying distribution system of pipe line, rising main, construction of Pump House, boudnary wall, providing functional House hold tap connection (FHTC) and allied works for Augmentation of MANDALAGURI (Zone-I & Zone-II) Piped Water Supply Scheme under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000096/2023-2024 | 1081/SWSD | 02/08/2023 | 14/03/2024 | M/S BIJAN KUMAR DUTTA | 386.79 | 0 | 0 | 4
5 | DARJEELING |  | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000031/2024-2025 | 563/CDD | 07/08/2024 | 07/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Renovation of the pump House and Others allied Works at Mandalaguri (H/W) site of Mandalaguri Piped Water Supply Scheme under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000144/2024-2025 | 2538/SWSD | 18/09/2024 | 02/11/2024 | K.K.GHOSH & CO. | 3.2 | 0 | 0 | 0
7 | DARJEELING |  | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | New Service Connection Charge for MANDALAGURI, T/W-I, under MATIGARA CCC, [APPLICATION NO. 4003340645, Reference ID : 403163196] |  |  | BILL/02138/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.1 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Installation of two tank chlorination system at MANDALAGURI and other adjacent water supply scheme UNDER JJM under MATIGARA Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. |  | Junior Engineer | ORD/000889/2024-2025 | 81/SMSD | 07/02/2025 | 17/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 1.1 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 05/02/2025 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
Total | [13 empty] | 528.59 | 0 | 0