## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 2059/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 23.85 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) |  | ORD/000048/2023-2024 | 241/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.76 | 3.74 | 99.6 | 100
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , TW No I (Zone-I) and TW No. I (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000786/2023-2024 | 1650/NMD | 29/09/2023 | 29/10/2023 | SUBHRANGSHU GUHARAJA | 11.58 | 7.04 | 60.77 | 50
4 | DARJEELING |  | Central Drilling | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Repairing Of Damaged House Connection Under Lalman Water Supply Scheme Under Siliguri Sub Division, Phe Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000188/2023-2024 | 1948/SWSD | 16/10/2023 | 26/10/2023 | SEBU CHAKRABORTY | 1.62 | 1.38 | 85.05 | 100
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 16/03/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 5 | 23.17 | 50
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT LALMON T.W NO:- IV UNDER NMD, PHE DTE. |  |  | BILL/01030/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.53 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | New Service Connection Charge for LALMAN (AUG), T/W-I, under BAGDOGRA CCC, [APPLICATION NO. 4003347057, Reference ID : 403169281] |  |  | BILL/02178/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.29 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Laying of pipeline for distribution system, rising main, construction of Pump House, Installation of I.E. Plant with blower room construction of boundary wall for Zone-I & Zone-II for Augmentation of LALMAN W/S Scheme under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000047/2023-2024 | 649/SWSD | 15/06/2023 | 10/02/2024 | S.G.CONSTRUCTION. | 453.84 | 91.75 | 20.22 | 65
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001067/2024-2025 | 35/NMD | 06/01/2025 | 05/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0 | 0
12 | DARJEELING |  | Central Drilling | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22045.96 | 108.9 | 0.49