## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 2045/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 16.3 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BAGULAHAGI & BHATTAGACHH PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000057/2023-2024 | 250/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.92 | 2.9 | 99.49 | 100
3 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319706, Reference ID : 403147081] |  |  | BILL/01933/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.67 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319825, Reference ID : 403147074] |  |  | BILL/01934/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.77 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Laying Rising main, laying distribution pipeline with functional household Tap connection (FHTC), construction of two number pump house (5.40 X 3.60 m), Iron Elimination plant (IEP) with Blower Room and sinking of 2 (two) Nos.Tube Well (ODEX- 165 method) and boundary wall for BAGULAHAGI and BHATTAGACHH PWSS Block - Kharibari, Dist : Darjeeling under Siliguri Sub Division , P.H.E. Dte. Sl No 07. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000076/2023-2024 | 867/SWSD | 14/07/2023 | 11/11/2023 | NARENDRA KUMAR | 197.75 | 110.85 | 56.05 | 25
6 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 05/02/2025 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAGULAHAGI and BHATTAGACHH PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000810/2023-2024 | 1667/NMD | 29/09/2023 | 13/03/2025 | MALAY KUMAR SAHA | 11.86 | 11.83 | 99.77 | 100
Total | [13 empty] | 403.02 | 125.58 | 31.16