## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2035/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 16.3 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Construction of Pump House 2 Nos., Rig bore 2 Nos. big dia T/W by Odex- 165 method, boundary walls, laying distribution system (HDPE pipe), rising main, providing FHTC & supplying fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (20 m cum/hr) and allied works at Augmentation of Buraganj & Jatru PWSS at Kharibari block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000010/2023-2024 | 335/SWSD | 08/05/2023 | 01/02/2025 | DEBRAJ ENTERPRISE | 228.26 | 202.39 | 88.67 | 100
3 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BURAGANJ & JATUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000060/2023-2024 | 253/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.22 | 3.22 | 100 | 100
4 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BURAGANJA and JATRU PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000783/2023-2024 | 1647/NMD | 29/09/2023 | 01/07/2025 | SANJIB SAHA | 11.85 | 7.57 | 63.91 | 100
5 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003291396 ; Reference ID : 403123842] |  |  | BILL/01712/2023-2024 | BP/23-24/202 | 27/12/2023 | 27/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003291407 ; Reference ID : 403123844] |  |  | BILL/01713/2023-2024 | BP/23-24/203 | 27/12/2023 | 27/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.06 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BURAGANJA AND JATRU PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001632/2023-2024 | 657/NMD | 15/03/2024 | 02/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 12.27 | 11.78 | 95.97 | 100
8 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 05/02/2025 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
Total | [13 empty] | 397.3 | 224.96 | 56.62