## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2035/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 16.3 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BURAGANJ & JATUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000060/2023-2024 | 253/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.22 | 3.22 | 100 | 100
3 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003291407 ; Reference ID : 403123844] |  |  | BILL/01713/2023-2024 | BP/23-24/203 | 27/12/2023 | 27/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.06 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003291396 ; Reference ID : 403123842] |  |  | BILL/01712/2023-2024 | BP/23-24/202 | 27/12/2023 | 27/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 05/02/2025 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Construction of Pump House 2 Nos., Rig bore 2 Nos. big dia T/W by Odex- 165 method, boundary walls, laying distribution system (HDPE pipe), rising main, providing FHTC & supplying fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (20 m cum/hr) and allied works at Augmentation of Buraganj & Jatru PWSS at Kharibari block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000010/2023-2024 | 335/SWSD | 08/05/2023 | 01/02/2025 | DEBRAJ ENTERPRISE | 228.26 | 202.39 | 88.67 | 100
8 | DARJEELING |  | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BURAGANJA and JATRU PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000783/2023-2024 | 1647/NMD | 29/09/2023 | 01/07/2025 | SANJIB SAHA | 11.85 | 7.57 | 63.91 | 100
Total | [13 empty] | 385.03 | 213.18 | 55.37