## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 2034/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 15.33 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000063/2023-2024 | 256/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.65 | 0 | 0 | 100
3 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | New Service Connection Charge for GANGARAM TEA GARDEN, T/W I, under BAGDOGRA CCC [APPLICATION NO. 4003221633, Reference ID : 403068165] |  |  | BILL/01117/2023-2024 | BP/23-24/122 | 10/10/2023 | 10/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF GANGARAM TEA GARDEN AREA PIPED WATER SUPPLY SCHEM , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 1375/NMD | 09/08/2023 | 08/09/2023 | NIRMAN | 20.9 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | New Service Connection Charge for GANGARAM TG, T/W No. II (AUG), under BAGDOGRA CCC [APPLICATION NO. 4003263578, Reference ID : 403103790] |  |  | BILL/01653/2023-2024 | 23-24/173&174 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.75 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Construction of 100 Cu.M. capacity R.C.C. Elevated Reservoir of 20 Mtrs. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells, construction of pump houses with toilet, boundary wall at head works and 2nd tubewell site with necessary interconnection, providing FHTC with platform and other allied works under Jal Jeevan Mission for Augmentation of GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME of Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000044/2023-2024 | 670/SWSD | 16/06/2023 | 26/07/2025 | RAJEEV RANJAN OJHA | 224.95 | 0 | 0 | 70
7 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 05/02/2025 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | Augmentation | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with Augmentation of Gangaram PIPED WATER SUPPLY SCHEME under Phansidewa block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000011/2025-2026 | 1237/SWSD | 24/04/2025 | 24/05/2025 | RAJEEV RANJAN OJHA | 11.94 | 0 | 0 | 0
Total | [13 empty] | 476.41 | 0 | 0