## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2043/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 14.57 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of two numbers pump house (5.40 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and boundary wall for ARJUNMAHAL PWSS, Block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000003/2023-2024 | 58/SWSD | 10/04/2023 | 08/08/2023 | M/S UTPAL CHAKRABORTY & CO. | 180.13 | 48.51 | 26.93 | 30
3 | DARJEELING |  | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ARJUN MAHAL PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000056/2023-2024 | 249/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.83 | 2.8 | 98.94 | 100
4 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ARJUNMAHAL PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2023-2024 | 1649/NMD | 29/09/2023 | 29/10/2023 | M/S UTPAL CHAKRABORTY & CO. | 11.85 | 11.81 | 99.71 | 100
5 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | New Service Connection Charge for ARJUN MAHAL, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193675, Reference ID : 403046163] |  |  | BILL/00597/2023-2024 | BP/23-24/77 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | New Service Connection Charge for ARJUN MAHAL, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208346 ; Reference ID : 403057205] |  |  | BILL/00993/2023-2024 | BP/23-24/94 | 29/08/2023 | 29/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ARJUNMAHAL PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001620/2023-2024 | 658/NMD | 15/03/2024 | 04/02/2025 | M/S UTPAL CHAKRABORTY & CO. | 12.27 | 11.57 | 94.28 | 100
8 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Quotation For New service Connection at Arjun Mahal Piped Water Supply Scheme, PH-II under Northern Mechanical Division ,PHE dte. siliguri. APPLICATION NO:- 4003208346 Reference ID :- 403057205 |  |  | BILL/00183/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 05/02/2025 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
Total | [13 empty] | 385.08 | 74.69 | 19.4