## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 2036/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 15.11 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF CHUCHUR MUCHUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000059/2023-2024 | 252/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.71 | 2.71 | 100 | 100
3 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. II under KHARIBARI CCC, [APPLICATION NO. 4003193651, Reference ID : 403046162] |  |  | BILL/00592/2023-2024 | BP/23-24/78 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193712, Reference ID : 403046161] |  |  | BILL/00593/2023-2024 | BP/23-24/78 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Construction of Pump House 2 Nos. Rig Bord 2 nos. big dia T/W by Odex-165 method, Boundary walls, Laying distribution system HDPE pipe, rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (three) month trial run IEP (20 cu.m./hr) and allied works for Augmentation of Chuchur Muchur PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000272/2022-2023 | 2576/SWSD | 23/02/2023 | 08/06/2023 | UJJWAL ROY | 142.67 | 139.6 | 97.85 | 95
6 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHUCHUR MUCHUR PWSS , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000069/2023-2024 | 644/NMD | 29/05/2023 | 28/06/2023 | PRATIK ROY | 23.35 | 23.28 | 99.71 | 100
7 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 05/02/2025 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
Total | [13 empty] | 352.89 | 165.59 | 46.92