## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 2037/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 13.5 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000061/2023-2024 | 254/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.77 | 0 | 0 | 100
3 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | New Service Connection Charge for RANGALI, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208340 ; Reference ID : 403057204] |  |  | BILL/00992/2023-2024 | BP/23-24/95 | 29/08/2023 | 29/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.16 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | New Service Connection Charge for RANGALI, T/W I, under KHARIBARI CCC [APPLICATION NO. 4003208350 ; Reference ID : 403057203] |  |  | BILL/00994/2023-2024 | BP/23-24/95 | 29/08/2023 | 29/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.11 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Construction of l00 cu.m. capacity RCC Elevated Reseervoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of 2 (two) nos. pump house (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and soil investigation at H/W site for RANGALI PWSS, block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000316/2022-2023 | 2918/SWSD | 24/03/2023 | 01/04/2025 | M/S BIRAT CONSTRUCTION | 217.11 | 0 | 0 | 10
6 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 05/02/2025 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall at H/W & 2nd T/W Site Augmentation RANGALI PWSS SCHEME Block Kharibari under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000019/2025-2026 | 1361/SWSD | 05/05/2025 | 04/06/2025 | S.G.CONSTRUCTION | 18.14 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2023-2024 | 1646/NMD | 29/09/2023 | 08/02/2025 | TAPAN BISWAS | 10.99 | 0 | 0 | 100
Total | [13 empty] | 479.57 | 0 | 0