## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1952/SWSD | 07/12/2022 | 07/12/2022 | Resource Division | 13.74 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR BANSGAON KISMAT PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000062/2023-2024 | 255/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 3.31 | 3.31 | 100 | 100
3 | DARJEELING |  | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Issue of fuel for office Executive Engineer and Assistant Engineer Siliguri W/S Division PHE Dte. |  |  | BILL/00295/2023-2024 | BP-2023-24-141 | 15/12/2023 | 15/12/2023 | SONA PETROL PUMP | 0.2 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR BANSGAON KISMAT (ZONE-I) TW No. I and II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2023-2024 | 1645/NMD | 29/09/2023 | 29/10/2023 | SARKAR ELECTRIC | 20.65 | 18.16 | 87.96 | 85
5 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] |  |  | BILL/01814/2023-2024 | BP/23-24/274 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.16 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320186, Reference ID : 403148656] |  |  | BILL/01949/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.11 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No.I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003320164, Reference ID : 403149648] |  |  | BILL/01948/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Construction Of 150 Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection ,rising main ,pump house (3 nos),IEP (2 nos.),Boundry wall, tube well and soil investigation test under Jal Jeevan Mission of UTTAR BANSGAON KISMAT Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000083/2023-2024 | 976/SWSD | 25/07/2023 | 14/03/2026 | MANAS KUMAR SAHA | 391.69 | 121.93 | 31.13 | 12
9 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 05/02/2025 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
12 | DARJEELING |  | Central Drilling | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 16.91 | 0.08 | 11
Total | [13 empty] | 21985.46 | 160.31 | 0.73