## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kharibari | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 2040/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 16.12 | 0 | 0 | 0
2 | DARJEELING | Kharibari | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF SONA CHANDI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000064/2023-2024 | 257/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.56 | 2.56 | 100 | 100
3 | DARJEELING | Kharibari | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 69/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 2.56 | 0 | 0 | 0
4 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | New Service Connection Charge for SONA CHANDI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319753, Reference ID : 403147078] |  |  | BILL/01951/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.2 | 0 | 0 | 0
5 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | New Service Connection Charge for SONA CHANDI, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319880, Reference ID : 403147076] |  |  | BILL/01950/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0 | 0
6 | DARJEELING | Kharibari | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Construction of Pump House 2 nos, Rig bord 2 nos big dia T/W by Odex -165 method, Boundary walls, Laying distribution system (HDPE pipe), rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (Three) month trial run IEP (25 cum/hr) and allied works for Augmentation of Sona Chandi PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 09/SWSD | 05/04/2023 | 19/07/2023 | A.K.CONSTRUCTION | 115.86 | 0 | 0 | 60
7 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sona Chandi Piped Water Supply Scheme, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2023-2024 | 1476/NMD | 17/08/2023 | 01/10/2025 | T S CONSTRUCTION | 24.83 | 0 | 0 | 90
8 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 05/02/2025 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
9 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
10 | DARJEELING | Kharibari | Northern Mechanical | Sona Chandi Piped Water Supply Scheme | SM/13436 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
Total | [13 empty] | 326.63 | 2.56 | 0.78